## ANNEX 1
LOGFRAME TABLE
Level | Narrative Summary | Activities | Indicators | Baseline | Target (6 Months) | Means of Verification | Assumptions
Impact | Improved academic performance and literacy among primary school learners | - Implementation of home-based learning support by facilitators | % improvement in literacy and exam scores | <50% | ≥20% improvement | School reports, exam results, teacher assessments | Learners attend school and participate in home learning
Outcome 1 | Increased parental and community involvement in home learning | - Community sensitization and mobilization- Household support by facilitators | % of learners receiving structured home support | <30% | ≥70% | Household surveys, facilitator reports | Parents and guardians are willing to participate
Outcome 2 | Improved literacy and facilitation skills among community members | - Training of community facilitators- Mentorship and follow-up support | % of trained facilitators demonstrating improved literacy and facilitation skills | Not measured | ≥60% | Pre/post training assessments, facilitator reports | Participants complete training and apply skills
Output 1 | 50 Community facilitators trained | - Conduct 2–3 training sessions on literacy and facilitation | Number of facilitators trained | 0 | 50 facilitators | Attendance registers, training reports | Trainers available; participants attend full sessions
Output 2 | Localized learning materials developed | - Develop 5 localized reading and learning materials | Number of materials developed and distributed | 0 | 5 materials; 50 copies distributed | Material samples, distribution logs | Technical and content support available
Output 3 | Community learning support structures established | - Formation of 10 active community learning groups | Number of active learning groups | 0 | ≥10 groups active | Field reports, facilitator logs | Community cooperation and leadership support
Activity 1 | Conduct community mobilization and sensitization | Directly linked to: Output 3 → Outcome 1 → Impact | Number of meetings conducted | 0 | 3 meetings | Attendance sheets, meeting reports | Local leaders support mobilization
Activity 2 | Train community facilitators | Directly linked to: Output 1 → Outcome 2 → Impact | Number of sessions, facilitator competency level | 0 | 4–5 sessions; ≥60% skilled facilitators | Training reports, pre/post tests | Trainers available; participants engaged
Activity 3 | Develop localized learning materials | Directly linked to: Output 2 → Outcome 2 → Impact | Number of materials developed and used by facilitators | 0 | 5 materials | Materials, distribution records | Materials are culturally relevant and accessible
Activity 4 | Implement home learning support activities | Directly linked to: Output 1, Output 3 → Outcome 1 & 2 → Impact | Number of households reached | 0 | ≥250 households | Facilitator logs, household reports | Facilitators consistently visit and support learners
Activity 5 | Conduct monitoring and evaluation | Directly linked to: All outputs and outcomes → Impact | Number of M&E visits, reports produced | 0 | ≥5 monitoring visits | M&E reports, field visit logs | Data collected regularly; corrective actions applied
Cross-Cutting 1 | Gender inclusion in participation | Integrated in all activities | % female facilitators | Not tracked | ≥50% | Attendance records | Equal opportunity encouraged
Cross-Cutting 2 | Sustainability through domino effect | Integrated in training & household support | # of facilitators replicating training | 0 | ≥50% | Facilitator reports | Community ownership maintained

## ANNEX 2
WORKPLAN TABLE
Activity | Sub-Activity | Responsible Person/Team | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Milestones / Deliverables
1. Community Mobilization & Sensitization | Identify key stakeholders and community leaders | Project Coordinator | X | [5 empty] | Stakeholders identified
| Conduct community meetings | Teachers & Coordinators | X | X |  |  |  |  | ≥2 sensitization meetings held
| Recruit participants (facilitators, households) | Teachers & Community Leaders | X | X |  |  |  |  | 50 community facilitators recruited, 250 households mapped
2. Training of Community Facilitators | Develop training modules and materials | Teachers | X | X |  |  |  |  | 5 localized learning modules prepared
| Conduct training sessions | Teachers & Trainers | X | X |  |  |  |  | 50 facilitators trained
| Pre- and post-training assessment | M&E Officer | X | X |  |  |  |  | ≥60% of facilitators demonstrate improved skills
3. Development of Localized Learning Materials | Draft and review content | Teachers & Curriculum Specialists | X | X |  |  |  |  | 5 learning materials finalized
| Print and distribute materials | School Administration |  | X |  |  |  |  | 50 copies distributed to facilitators
4. Home Learning Support Implementation | Assign households to facilitators | Project Coordinator |  | X |  |  |  |  | Each facilitator assigned ≥5 households
| Conduct home learning support sessions | Community Facilitators |  |  | X | X | X |  | ≥250 households reached; weekly learning sessions conducted
| Monitor and support facilitator performance | Teachers & Project Coordinator |  | X | X | X | X | X | Weekly reports from facilitators; mentorship provided
5. Monitoring & Evaluation | Baseline assessment of learners | M&E Officer | X | X |  |  |  |  | Baseline assessment completed
| Monitoring visits | M&E Officer & Project Team |  | X |  | X |  | X | 5 field visits conducted; reports generated
| Endline assessment and project evaluation | M&E Officer | [5 empty] | X | Endline assessment completed; impact measured
6. Reporting & Documentation | Monthly progress reports | Project Coordinator | X | X | X | X | X |  | Monthly reports compiled
| Final project report | Project Coordinator & M&E Officer | [5 empty] | X | Comprehensive project report submitted

## ANNEX 3
MONITORING AND EVALUATION FRAMEWORK
Level | Indicator | Target | Data Source | Data Collection Tool | Frequency | Responsible | Assumptions / Risks
Impact | % improvement in literacy & academic performance | ≥20% improvement | School assessment reports, teacher records, exams | Endline assessment form | Month 6 | M&E Officer & School Principal | Learners attend school and participate in home learning
Outcome 1 | % of learners receiving structured home learning support | ≥70% of learners supported | Household surveys, facilitator reports | Household survey form | Monthly | Project Coordinator & M&E Officer | Parents and guardians actively support learning
Outcome 2 | % of trained facilitators demonstrating improved literacy & facilitation skills | ≥60% | Pre/post training tests, observation | Training assessment checklist | After training & monthly follow-up | M&E Officer & Trainers | Participants complete training and apply skills
Output 1 | Number of community facilitators trained | 50 facilitators | Training attendance registers | Attendance sheets | After each training session | Trainers / Teachers | Trainers available; full participant attendance
Output 2 | Number of localized learning materials developed & distributed | 5 materials, 50 copies | Material inventory, distribution records | Inventory sheet, distribution log | Quarterly | Project Coordinator | Materials are culturally relevant & accessible
Output 3 | Number of active community learning groups | ≥10 groups | Field reports, facilitator logs | Facilitator logbook | Monthly | Community Facilitators & M&E Officer | Community cooperation and leadership support
Activity 1 | Number of community mobilization meetings conducted | ≥2 meetings | Attendance sheets, meeting reports | Meeting minutes / registers | Monthly | Project Coordinator | Community leaders support mobilization
Activity 2 | Number of facilitator training sessions conducted | 5 sessions | Attendance sheets, training reports | Attendance registers | After each session | Trainers | Trainers available; participants engaged
Activity 3 | Number of households reached through home learning support | ≥250 households | Facilitator logs, household reports | Household tracking form | Monthly | Community Facilitators | Facilitators visit assigned households consistently
Activity 4 | Number of monitoring visits conducted | ≥5 visits | Field visit reports | Field monitoring checklist | Monthly | M&E Officer | Transport and logistics available
Cross-Cutting | % female participation among facilitators | ≥50% | Training attendance sheets | Attendance registers | After training | Project Coordinator | Gender equality promoted and encouraged
Cross-Cutting | Number of facilitators replicating training (domino effect) | ≥50% of facilitators | Facilitator reports | Replication tracking form | Monthly | Project Coordinator | Community ownership maintained

## ANNEX 4
BUDGET TABLE
Budget Category | Budget Code | Description / Items | Unit Cost ($) | Quantity | St. Michael Int NPS ($) | Cavendish Uni Ug ($) | Total ($) | Justification
1. Community Mobilization & Sensitization | 1.1 | Transport for facilitators & teachers to community meetings | 110 | 2 trips | 220 | 0 | 220 | Ensures participation and mobilization of 250 households
| 1.2 | Refreshments for community meetings | 110 | 2 sessions | 220 |  | 220 | Provide light refreshments for participants, encourage attendance
| 1.3 | Printing of sensitization flyers | 10 | 1 banner | 10 |  | 10 | Awareness raising and recruitment of facilitators
2. Training of Community Facilitators | 2.1 | Training venue / space (school hall) | 20 | 5 sessions | 100 |  | 100 | Local venue for facilitator training sessions
| 2.2 | Training materials (paper, pens, markers) | 1 | 50 participants |  | 50 | 50 | Supplies for hands-on training exercises
| 2.3 | Trainer stipends / incentives | 10 | 5 sessions |  | 50 | 50 | Motivates teachers / trainers to conduct sessions
3. Development of Localized Learning Materials | 3.1 | Content development & review | 10 | 5 materials |  | 50 | 50 | Teachers & curriculum specialists’ time for creating localized materials
| 3.2 | Printing & photocopying | 2 | 50 copies |  | 100 | 100 | Materials for facilitators and households
4. Home Learning Support Implementation | 4.1 | Transport for facilitators to households | 50 | 20 trips | 1000 |  | 1000 | Ensures facilitators reach all assigned households
| 4.2 | Refreshments for facilitator visits | 50 | 20 sessions | 1000 |  | 1000 | Minimal support for facilitator morale during visits
5. Monitoring & Evaluation | 5.1 | Field visits by M&E officer | 50 | 4 visits |  | 200 | 200 | Covers transport and minor allowances for data collection
| 5.2 | Data collection tools (forms, registers) | 5 | 4 sets |  | 20 | 20 | For baseline, monitoring, and endline assessment
6. Reporting & Documentation | 6.1 | Printing reports and documentation | 5 | 6 reports |  | 30 | 30 | Monthly progress and final project report printing
7. Contingency / Miscellaneous | 7.1 | Unexpected minor expenses | 50 | 1 | 50 |  | 50 | For any unforeseen small costs during implementation
TOTAL |  |  |  |  | 2600 | 500 | 3100